Technology Plan

For

Lyons Central School district

2007-2010

# Table of Contents

## Foreword………………………………………………	page 3

## Acknowledgements………………………………….	page 4

## Technology Committee……………………………..	page 4

## Methodology and Current Status………………...	.page 5

## Objectives and Goals…………………………………….	page 8

Technology Budget………………………………………………………………page 18

## Appendix -Policies and Procedures: ……………..	... .page 21

### District Acceptable Use Policy……………………………………Appendix A

### Staff Computer Usage Policy…………………………………….Appendix B

### Student Social Web Page Usage Policy………………………..Appendix C

Staff Social Web Page Usage Policy……………………………Appendix D

District E-mail Policy………………………………………………Appendix E

### District Web Page Policies……………………………………….Appendix F

### Loan of District Technology Equipment Policy and Form….....Appendix G

Loan of District Technology Equipment during summer months/extended vacations……………………………………………………………Appendix H

Foreword

The Board of Education of the Lyons Central School District has committed itself to ensuring that each student will be:

- A Self Directed Learner

- A Critical Thinker and Problem Solver

- Academically Proficient

- A Responsible Citizen

- An Effective Communicator

In order to ensure that each student graduates with the information and skills needed to exist in a technologically advanced society, the Board of Education recognizes the need to integrate technology throughout students’ educational experiences.  The Board of Education’s commitment to providing updated and accessible technology is essential not only for a strong technology program but for a comprehensive education that incorporates technology throughout.

In terms of technological growth, our school district can be proud of the progress made over the past ten years.  It is only with the continued support of the Board of Education that we will continue forward movement.

Acknowledgements

The Lyons Central School District’s Technology Planning Committee acknowledges the following for their support.

# The Board of Education

- Rick Amundson, Superintendent

- David Alena, Asst. Supt. For Business

- Mark Cazer, Project Manager, EduTech

- Anyone else who provided input regarding the technology needs for the district.

Lyons Central School Technology Planning Committee

## Bill DiCicco	Assistant Supt. For Business

Kathie Polyn	Computer Coordinator

Steve Leo	Network Administrator

Mark Schermerhorn	H.S. Technology Teacher

Brenda Neal	Elementary Computer Teacher

Tom Mancine	Elementary Music Teacher

Nina George………………………………………………………..Elementary Librarian

Denise Chilson-Cline	Middle/High School Librarian

Anne Cook	First Grade Teacher

Nate Wolf………………………………………Math & Science Technology Teacher

David Wasnock ….......................Middle School Science Teacher/Electronic Information Processing Teacher

Bridgette Waldron………………………………………… …Living Environment Teacher/SIT Committee

Methodology & Current Status

In the fall/winter of 2007 the Technology Committee met to review our past Technology plan.  Many of the goals from our previous plan had been attained while others were ongoing and have become part of this plan.  Furthermore, with changing technologies some new goals have been added.

Since the last Plan was adopted three years ago Lyons School District has made significant gains in technology.

The District now has its’ own external Community TV channel which is shared with eleven other school Districts.  In addition to this the District also has an internal TV channel for broadcasting school news at the Middle/High School.  A Broadcasting/Journalism class produces live school news to this channel which can be viewed during the day on Television sets located in halls throughout the building. This year the District has implemented a new mass communication system that can be used by Administrators to inform parents of emergency closings, school news and other important school events.  This communication system can send messages via telephone and or email.  The system also informs the District of non-working phone numbers enabling the District to maintain more accurate student information.

The school implemented an automated Lunch Program last year.  Students order lunch using a pin number.  This system also tracks critical student information for the District.

The District with BOCES assistance continues to add and modify additional student tracking information systems to comply with State Ed requirements.

The District now has wireless carts, one for each building level.

The Junior/Senior High School has the following technology:

- Two wireless carts, one for Middle School Classroom use and one for High School Classroom use

- MST lab (12 computers)

- Cad lab	(17 computers)

- PC lab (28 computers)

- Business/ Art Lab (23+ 9 computers)

- Library Lab (14 computers)

- All District file servers (4 )

- Laptops for staff (6)

- 9 digital cameras

- 3 camcorder

- 1 DV camcorder

- 17 projectors

- Each classroom has 6 network drops

- At least 1 computer workstation

- HS Resource room has a mini lab (6 computers)

- MS Resource room has 1 computer and 1 laptop

- 7 scanners

The Elementary School

- 1 wireless laptop cart house in Elementary Library

- Computer lab (28 computers) Mac OS X

- Second computer lab  (20 workstations)

- All classroom teachers and support staff have a pc workstation

- 6 network drops per classroom

- Grades 4-6 have one pc for student use.

- Primary grades K-3 have Apple  MAC work centers in

- 6 Digital Cameras

- 1 DV camcorder

- 6 projectors

- 2 Laptops

- 2 scanners

Out of School Suspension Facilities –

10 Computers on a separate network

Bus facilities

Workstations with wireless access to School Network & student records database system

# District Wide

- All buildings are networked

- Computer Coordinator

- Network Administrator

.

Objective 1:

Use telecommunications and information technology to improve education and library services.

Goals:

- Improving student access to technology.

- Increasing and improving integration of technology with curriculum to meet NY State Standards

- Analysis and Update of Technology Curriculum Objectives

Steps for Objective 1:

| Timeline | Solutions | Strategies/Steps | Training Needed/Support | Update/Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| 2007-2010 | More access to computer technology for educational purposes. | Computer(s) in the classroom for immediate researching, Computers for Classroom Centers in Primary grades for review of curriculum. Centrally located labs Computer carts for classroom use | Technical support to set up computers and software. Librarians training students to research databases. | Most recent computers in labs and libraries. Maintenance of Lab Carts for each building High School, Elementary and Middle School. | Technology Committee, Librarians, Technical support, Elementary Computer Teacher, and Technology Teacher |

| Timeline | Solutions | Strategies/Steps | Training Needed/Support | Update/Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| 2007-2010 | Continue analysis and selection of appropriate Educational Software, BOCES COSER research Databases Video streaming, Subscription for databases, teacher web based tools (web pages, quizzes) | Work with CDEP Plan to evaluate State test scores to determine areas of need. Use web base tools such as Data warehouse, Data mentor | Teachers review software to determine if it meets their needs. Curriculum coordinator evaluates software. Technical support evaluates compatibility with platforms. TIF* provide training | District continuing to use new software to meet students’ educational needs. | Curriculum coordinator, Technology Coordinator, Technology Committee |
| 2007-2010 | More curriculum integration utilizing current peripheral technologies (digital cameras, scanners, smart boards, video cameras) | Centrally located. Procedures and Policies in place for loan. | Backup personnel to assist in lending out equipment and assisting staff with usage, troubleshooting. | Review records of equipment loan to determine availability and usage. | Technology Coordinator, Library media staff, Lab teachers . |
| Ongoing | District Policies and Procedures in place for student access technologies | Update existing policies and procedures and establish any new ones as needed by the District. | BOCES, Other school Districts | Policies and procedures updated and added | Technology Committee |
| Ongoing | Update the computer curriculum objectives as needed | Review objectives | Requests by Staff | Documentation of Objectives | Tech. Committee Computer Coordinator |

Objective 2:

Implement a Professional Development Plan for learning new and existing technologies. This plan will also be incorporated into the existing district Professional Development Plan.

Goals:

- Provide teachers with the opportunity for technology training and curriculum integration.

- Provide support to teachers for implementing new technologies.

- Technology Professional Development Plan should integrate with overall District Professional Development Plan.

- Provide additional student/staff data collection tracking systems as needed for District and State reporting.

- Provide technical incentive program for those teachers who wish to do more with technology.

Steps:

| Timeline | Solutions | Strategies/Steps | Training Needed/Support | Update/Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Develop a technology proficiency level that all staff should meet | -Determine what staff needs to know to use technology -Determine the minimal technical skills requirements | Technology Committee will provide a plan and support. | Guideline for the District by end of school year 06-07. | Technology Committee |
| Ongoing | Develop and implement a staff training plan | - Incorporate the minimal technology skill levels through to the advanced skill levels -Update as necessary | Technology Committee | Superintendent’s Conference days, after school training, BOCES training | Technology Coordinator. Administrators, Curriculum Coordinator |
| Timeline | Solutions | Strategies/Steps | Training Needed/Support | Update/Evidence | Person(s) Responsible |
| Ongoing | Technology Training opportunities | - In-house training - Off-site training | BOCES/ Edutech, Teacher Resource Center | Professional Development Records maintained by the District. | Technology Coordinator/Administration |
| Ongoing | Financial Compensation for Training | - Release time - Finance Compensation | Mentor teachers in the District | Business Office Records | District |
| Ongoing | Utilize technology-oriented staff and mentor teachers to assist and serve as additional support staff | - Existing support staff will train and create a technical support team to assist other district personnel - Provide a list of staff and their technical skills on the technical support team to the district | -Technology-oriented staff. -Technology committee | -Training records indicate staff trainers. -List of ‘Technical skills staff’ prepared at the beginning of 07-08 and updated at the beginning of every school year. | Technology Committee |
| Ongoing | Continue to utilize technology support staff and develop other backup staff | Every skilled technology trainer should train a staff member and this should be indicated on the technical skills list. | Training time | Additional staff assisting the District, | Technology Committee and current District Technology trainers. |

| Timeline | Solutions | Strategies/Steps | Training Needed/Support | Update/Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Continue to incorporate technology goals into overall teacher goals | - Goal setting with principals/administration - Teacher incorporate a technology goal into PDP | -Administrative support/ time during -Superintendent Conference Days or training | -Professional Development Plans -Technology Training during Superintendent Days | Technology Committee |
| Ongoing | Continue to improve and add student tracking data for District | - AIS Edge web-based program for tracking AIS students - Data Warehouse | Available time for staff training such as Superintendent’s Conference Days | -AIS Edge implemented and used by the District -Data warehouse used by District | Technology Coordinator, Curriculum Coordinator |
| 07-09 | Laptops for Advanced Technical staff | -Explore possibility of giving advanced technology staff a District laptop with the provision that they will become turnkey technology trainers for the District | Explore a possible program and plan | A proposal | Technology Committee/ Administrators. |

Objective 3:   Assess the School District’s telecommunication services, hardware, software, and other services that will be needed to improve education or library services;

Goals:

- Develop a plan for the continuous updating of District technical equipment.

- Review and ensure that instructional software and educational web based sites needed for curriculum instruction are supported by the existing Districts hardware and operating systems.

- Assess facilities for Technological growth

- Review and update the Districts electronic communication systems.

- Review peripheral inventory including classroom projectors add, replenish, or repair as needed

- Review District printer/copier  requirements

- Review external media retrieval systems

- Review and update the Districts computerized security systems

- Review District policies and procedures

Steps for Objective 3:

| # Time line | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing 2010 | - Plan to remove outdated hardware and replenish inventory -Have District on PCs platform only by removing Macs at Elementary -Consider replacing labs with wireless cart. | Detailed plan identifying older models and a timeline to remove and update them including financing. -Determine staff responsible for maintenance. | Business Manager, Network Administrator, Technology Coordinator | Yearly updating or replacement of older equipment | Business Manager, Network Administrator, Technology Coordinator and Technology Committee |
| # Time line | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| Ongoing | Ensure that Districts operating systems and hardware support instructional software and educational web sites. | -Verify that new software specs and web sites comply with District operating systems/ hardware. -Develop a plan to accommodate for this growth. | Technology Coordinator Network Administrator | Software/ web sites able to run on District hardware. | Technology Coordinator Network Administrator, Technology Committee |
| Ongoing | Maintain hardware inventory for District. Maintain Software inventory for the District and system requirements | Maintain electronic records and use electronic resources for gathering data. | BOCES Software inventory | Records maintained by Technology | Technology Coordinator and Network Administrator |

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| # Ongoing | Provide technology resources for new relocated and renovated classrooms | Meet with architects, staff, BOCES, Administrators to determine plans Evaluate other schools facilities | Architect needs to understand expectations & incorporate in his design | New classrooms with plenty of space for technology | Admin. Computer Coordinator Tech Committee |
| # Ongoing | Examine network infrastructure and update as needed | Meet with BOCES to determine needs analysis | BOCES network staff | Servers and network working efficiently | Computer Coordinator Network Administrator |
|  | Examine wireless network feasibility across district | Contact BOCES/Outside vendor |  |  |  |
| # Ongoing | Review District communication systems and add/ update or eliminate as needed -Email system -Communication to parents: Web site/student grades, Mass phone communication system/school TV channel | Explore enhancements to current technologies, Examine newer technologies Proposals | Administrators Teachers Support Staff Web Master BOCES | Improved District communications to parents/students | Computer Coordinator, Network Administrator |
| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| Ongoing | Increase District classroom/department projectors. | Develop a plan to increase yearly projectors for the District | Business Manager, Technology Coordinator, Network Administrator | Increase in projectors for the District | Computer Coordinator Tech Committee |
| Ongoing | Analyze older peripheral equipment such as projectors, cameras and have a plan to replenish inventory as needed | Review inventory plan and determine replacement needs/ repairs. | Technology Committee, Business Manager | Repair records and new purchases of equipment. | Technology Committee |
| Ongoing | Develop a Cost effective plan for District Printers that accommodates staff/ students needs | -Analyze printing needs for the District. -Develop a long range plan for Staff /student use | BOCES Other school Districts | More uniform printers in District | Network Administrator, Technology Coordinator, Business Manager |
| 07-08 | Proposal for External media system | -Analyze external media systems -Review cost and feasibility for District | Technology Coordinator, Network Administrator, BOCES, Business Manager | Proposal | Technology Coordinator, Network Administrator, Business Manager |
| Ongoing | Review District security systems and update/replace as needed | -Examine updates to existing system -Analyze newer systems Proposals | Facilities, Network Administrator, Tech Coordinator, Vendors Business Manager | Upgrades/new systems | Business Manager, Tech Coordinator, Network Administrator |
| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| Ongoing | Policies and Procedures in Place for use of all Technology and District network access, storage of data, hardware usage, and email by District staff and students. | Documented policies and procedures. Revise as needed as well as add new policies and procedures. | Administrators | Documented in Technology Plan, Teacher handbooks, Student handbooks, School web site | Technology Committee, Technology Coordinator and Network Administrator |

Objective 4: Providing for a budget to obtain and maintain hardware, software, professional development and other services.

Objective 5:  Evaluate and monitor the progress toward ‘Objective goals’ and make mid-course corrections in response to new developments and opportunities as they arise.

Goals:

Determine if each Technology goals has been met and revise accordingly by reviewing ‘Update and Evidence’ in Technology Plan

Review Plan on a yearly basis with Technology Committee & update as necessary

Assess Student’s technological skills and ability to use technology independently for course work.

| # Timeline | Solutions | ### Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Knowledge & integration of District’s K-12 Technology curriculum | Integrate technology into portfolio development Elementary evaluation of curricular alignment MS – MST evaluate curricular alignment HS – 11th grade evaluate curricular alignment -Increased integration where feasible into curriculum instruction | Technology Committee supports building curriculum efforts focusing on technology integration | -Utilization of Technology curriculum -Students will demonstrate the use of technology in their benchmark presentations and at grade levels | Technology Committee Teaching Staff |
| Ongoing | Evaluate student technology skills and application | Students will be evaluated before & after grade levels to determine if curriculum objectives have been met. | Clear expectations of curriculum outcomes at each grade level | Students will improve technical skills | Building Principals |

Appendix

Appendix A.

Internet Usage

1. 	Internet access has been established for educational purposes only, which include classroom activities, career development, and educational research projects consistent with Lyons Central School District policy.

2. 	Students may not use the Internet for commercial purposes. Students may not offer, provide or purchase products or services through the Internet. Students may not use the Internet for Social sites such as My Space, You Tube, etc.

3. 	Students may not use the Internet for e-mail purposes unless it involves an educational project. The District has two generic email accounts available for all student use which are controlled by the lab assistant. One for MS/HS and one for LES, see lab assistant or Librarian for help.

4. 	Access to the Internet and to district computer technology is not a right but a privilege and unacceptable usage will result in revoking this privilege.

Lyons Central School District

Student Acceptable Use Policy

for Computer Technology

Overview

With Computer Technology comes an electronic network that provides vast, diverse and unique resources. Our goal is to provide teachers, staff, and students with up-to-date computer technology including access to the Internet. We believe however, that the use of this technology within the Lyons School District is a privilege, not a right, and that certain guidelines must be adhered to.

Guidelines

A. 	Educational Purpose

1. 	Internet access has been established for educational purposes only, which include classroom activities, career development, and educational projects consistent with Lyons Central School district policy.

2. 	Students are expected to follow the rules set forth in the Lyons MS/SR. High School Student Handbook/or Elementary building policies that may apply to the use of computer technology.

3. 	Students may not use the Internet for commercial purposes. Students may not offer, provide, or purchase products or services through the Internet.

4. 	Students may not use the Internet for e-mail purposes unless it is involving an educational project and under the supervision of the lab assistant.

B. 	Student Access.

1. 	All students will have access to the Internet World Wide Web information resources wherever available. Students in grades K-12 using the Internet will be under adult supervision.

- All students will have access to District computer technology.

- Access to the Internet and to district computer technology is not a right but a privilege and unacceptable usage will result in revoking this privilege.

- Students will have e-mail access only under adult supervision using one generic student account..

- Students training in safety and “etiquette “in the use of the Internet will be required before student use is allowed.

- Students should be familiar with Technology school/student copyright practices.

- Graduating/Transferring students may make a copy of their work on the school server account prior to their departure.  The District is not responsible for transmitting any of this data for the student once they have left the District.  Their server accounts will be eliminated after they have left the District.

- Student Multimedia Presentations

- Students’ multi media presentations (video/ still pictures and or power point)   that are to viewed in a public forum must first be reviewed by an Administrator and have his written approval before the student is allowed to do his presentation.

.

- Use of Non District software or  non educational downloads  is not permitted

- Use of Non District technology equipment in the District

- Students are not allowed to bring/use personal technology equipment in the District.  The school is not responsible for setting up their computers so that Internet access/server accounts can be reached.

F.. 	Unacceptable Uses

1. 	E-mail and the Internet

a. 	Students will not post personal contact information about themselves or other people. Personal contact includes information regarding home addresses, telephone, school address, work address, etc.

b. 	Students will not agree to meet with somebody they have met on-line.

c. 	Students will promptly disclose to their teacher or other school employee any message they receive that is inappropriate or makes them feel uncomfortable.

d.        Students will not access any remote servers to get out on the Internet other that the District network.

e.	Use of Non District software or non educational download are not permitted

2. 	Software

a. 	Students will not download software from the Internet.

b. 	Students will not make illegal copies of District software.

When software is purchased it is licensed for a particular computer or group of computers. To use software in a manner that is not in compliance with the software license is an infringement of copyright laws.

c. 	Students will not load software from floppies, CD-ROM, or external hard drives on to District Computers.

3.	 Illegal Activities

a. 	Students will not attempt to gain unauthorized access to any other computer systems through the Internet access, or go beyond authorized access. This includes attempting to log in through another person’s account or access another person’s files. These actions are illegal, even if only for the purposes of “ browsing “.

b. 	Students will not make deliberate attempts to disrupt the computer system or destroy data by spreading computer viruses or by any other means. These actions are illegal.

c. 	Students will not use the Internet to engage in any other illegal act, such as arranging for the sale or purchase of illegal drugs which includes alcohol and

cigarettes, engaging in criminal gang activity, or threatening the safety of person[s], etc.

4. 	System Security

a.	Students are responsible for their individual accounts and should take all reasonable precautions to prevent others from accessing their password.

b. 	Students will immediately notify an administrator or the technology coordinator if they have identified a possible security problem.

c. 	If a security problem is detected by a student, that student will not identify this problem to anyone other than those specified above.

d. 	Students will avoid the inadvertent spread of computer viruses by following the Lyons School District virus protection procedures.

e. 	Any other user identified as a security risk may be denied access.

5. 	Inappropriate Language

- Students will not use obscene, profane, lewd, vulgar, rude, inflammatory, threatening, or disrespectful language on the computer.

- Students will not post information that could cause damage or danger of 	disruption to the computer network.

c. 	Students will not engage in personal attacks, including those that are prejudicial or discriminatory.

d. 	Students will not harass another person. Harassment is persistently acting in a manner that distresses or annoys another person. If a student is told by a person to stop sending them messages, the student will do so.

e. 	Students will not knowingly or recklessly post or defamatory information about a person or organization.

6. 	Respecting Resource Limits

a. 	Students will use the system only for educational and career development activities.

- Students will not download files to the computer unless approved by a supervising adult.

c. 	Time allocation is set for each student by attending supervisor.

7. 	Plagiarism and Copyright Infringement

a. 	Students will not plagiarize works on the Internet. Plagiarism is taking the ideas or writings of others and presenting them as if they were theirs.

b. 	Students will respect the rights of copyright owners. Copyright infringement occurs when someone inappropriately reproduces a work that is protected by a copyright. If a work contains language that specifies appropriate use of that work, students should follow the expressed requirements. If students are unsure whether or not work can be used, consult with a teacher or librarian.

8. 	Access to Inappropriate Material

a. 	Students will not use the Internet or any other computer technology to access material that is pornographic or obscene. Students will not access material that advocated illegal acts, violence or discrimination towards other people.

b.	 If a student mistakenly, accesses inappropriate information, that student should immediately tell a teacher, administrator or technology coordinator. This will be documented and will protect the student against a claim that student has intentionally violated this policy. However, if a student repeatedly accesses inappropriate information, a review will be done to determine if access was truly accidental.

c. 	If there is material that a parent feels inappropriate for their child to use, the Lyons School District fully expects that the student will follow their parent’s instructions in this matter.

G. 	Students rights

1. 	Free speech

Technology communication is considered a limited forum, similar to the school newspaper and the Lyons school District may restrict student’s speech for valid educational reasons.

2. 	Search and Seizure

a. 	Students should expect only limited privacy in the contents of their personal files on the Lyons School District system. Teachers, administrators and the technology coordinator will have access to all student files on the Lyons School District’s instructional network. This excludes administrator’s files pertaining to the student’s personal information.

b.	Routine maintenance and monitoring of the Lyons School District’s networks may lead to discovery that a student has violated this policy, as stated in the Student Handbook, or the law.

c. 	An individual search will be conducted if there is reasonable suspicion that a student has violated; Student Acceptable Use Policy for Use of computer Technology, Student Handbook, or the law.

d. 	Parents have the right at any time to request to see the contents of their child’s account.

e. 	Network storage areas may be treated like school lockers. Network administrators may review files and communications to maintain system integrity and insure that

users are using the systems responsibly. Users should not expect that files stored on district servers will always be private.

3. 	Due Process

a. 	The Lyons School District will cooperate fully with local, state, or federal officials in any investigation related to any illegal activities conducted through the Internet or the Lyons School District Network[s].

b. 	In the event there is a claim that a student has violated this policy in the use of   computer technology, the student will be provided with the written notice of the suspected violation and an opportunity to be heard in the manner set forth in the Lyons Central School Student Handbook.

c.	Lyons School District administrators will make the final determination as to what constitutes unacceptable use and their decision is final.

d. 	If the violation also involves a violation of other provisions of the Lyons Central School Student Handbook, it will be handled in a manner described in the Lyons Central School Handbook. Additional restrictions may be placed on student’s use of their Internet account.

4.	Limitation of Liability

The Lyons School District makes no guarantee that the functions or the services

provided by or through the Lyons School District system will be error-free or

without defect. The Lyons School District will not be responsible for any damage

incurred, including but not limited to, loss of data or interruptions of service. The Lyons School District is not responsible for the accuracy or quality of the information obtained through or stored on the system. The Lyons School District will not be responsible for any financial obligations arising through the unauthorized use of the system.

5.	Personal Responsibility

It is the student’s responsibility to use computer technology, both inside and outside of school, in a proper, lawful fashion. Failure to use computer technology appropriately may result in any or all of the following depending on the infraction.

Verbal warning

Loss of Internet use

Limited use of computer technology

Loss of access to computer technology

Appendix B.

Staff Technology Usage Policy

Staff (Teachers and Support Staff) must also follow the same guidelines as indicated in the Student AUP guidelines and in addition must also adhere to the following District policies.

- District email system.

  - The District email account is provided to staff to enhance professional communications. It should for professional purposes and should not be used to solicit other business from staff. Personal use of e-mail should be limited to brief important messages, or emergency situation. (See Appendix E for more details.)

- Use of non District computer equipment, printers and scanners.

  - Staff may not connect their own personal peripherals to District workstations, such as printers.  If a staff member has their own digital camera with a memory card they may use a district card reader to get photos for their instruction.

- Jump drives

  - Teachers may use jump drives to take school work back and forth to home.

- Software

  - Only District software may be used on District computers.  The District has the right to remove any software it has not purchased and is found on a workstation.

- Student Information Systems

  - The teacher is responsible for keeping all student information that is on the school management systems (databases and web based platforms) secure. Teachers are responsible for closing out the programs when away from their computer.

- Equipment loan

  - All computer equipment that is loaned out to staff by the District is to be used for educational purposes only and should be returned within reasonable time frames and before the end of the school year.

- School web filtration system

  - Teachers are expected to use the school internet filtration system.  If an educational site is blocked and the teacher feels it would be beneficial to their curriculum, they may request for that site to be unblocked. The request should be given to the Technology Coordinator or Network Administrator. Teachers should test a site for restrictions at school and not at home, as restrictions vary.

  - If a teacher needs to bypass the filtration system for school research they may use a workstation in each library building that will allow this.  If a site becomes unblocked it will be unblocked district wide.

Appendix C

Student Social Web Page Usage Policy

The following policy refers to the usage of social networking sites such as MySpace, Facebook, and Friendster.

- The Lyons Central School District does not allow the use of such sites on school property and is not responsible for student use of social Web Sites off of school property.

Appendix D

Staff Social Web Page Usage Policy

The following policy refers to the usage of social networking sites such as MySpace, Facebook, and Friendster.

- District staff is responsible for monitoring student Internet usage during school hours.

- Personal use of social networking sites should be used with caution and common sense.

- Using password protection for personal networking pages is recommended.

Appendix E

District E-mail Policy

- All communications should be work related.

- Electronic mail is not private or secure.  Never write anything you would not put on a postcard. Never send any confidential or sensitive information.  Messages are very easy to forward to others.

- Do not send messages when you are angry or upset.  Give yourself time to calm down.

- Never send abusive, harassing or threatening messages.  Respect the laws governing copyright, defamation, and discrimination in written communication.

- Electronic communication offers no vocal intonation or facial expressions. Be careful using humor or sarcasm.  They do not translate well through e-mail.  A statement made in person may translate differently via e-mail.

- Messages and replies should be brief and to the point.  It may not be necessary to reproduce the entire message.  Be selective by only reproducing enough to establish the intent of the original message.

- Use e-mail in a professional manner.  Remember your mailbox is NOT private and is district property.

- Do not send chain letters or any message that request you forward it to other people.

- Never leave your e–mail account open if you leave your computer.  Realize anyone could send out offensive, embarrassing or libelous messages under your name.  Always LOG OFF!

- Due to legal and confidentiality concerns, “all staff” mail lists should be used with discretion and only for professional communications.

- Staff may create smaller distribution lists (small group mailing lists).  Be considerate when using distribution lists when sending messages or replies.  Be sure there is a very specific need for the members of the list to see the message.  For example, members of a science committee may want to use a distribution list containing all committee members.  Indiscriminate use of distribution lists can waste disk space, clutter up inboxes, and annoy other users.  Distribution lists should be created for work-related purposes only.

- If you are not able to provide a complete response to a message, acknowledging its receipt and giving a timeframe as to when you will get back to them is a common courtesy.

- The user should check for e-mail messages at least once a day.  The user should also regularly maintain their mailbox deleting old messages from all boxes. If keeping an old message is required consider cutting and pasting it to a Word document.

- Print out messages only when a hard copy is necessary.

Appendix F.

Web Page Policies

The availability of Internet access in the Lyons Central School District provides an opportunity for students and staff to contribute to the school district’s presence on the World Wide Web. These Web sites provide information to the world about school curriculum, instruction, school-authorized activities, and other general information relating to our schools and LCSD’s mission. Lyons Technology Committee provides Internet access for the creation of web pages. Creators of Web pages must familiarize themselves with and adhere to the following standards and responsibilities. Failure to follow these standards or responsibilities may result in the loss of authoring privileges or other more stringent disciplinary measures.

Approval for posting a page must be obtained from the Technology Coordinator. If at any time the principal, district technology coordinator, or any central office administrator feels the site does not meet the standards approved by the district, the site will lose its district privileges.

Content standards	2

Principal/District Approval Form	3

Teacher/Web Publisher Agreement	34

Parent Permission Form	35

# Content standards

- Web page documents may include only the first name of the student.

- Documents may not include a student’s phone number, address, names of other family members, or names of friends.

- Published e-mail addresses are restricted to staff members.

- Decisions on publishing student pictures still, audio clips or student work are based on the supervising teacher and the building principal’s judgment.

- Web page documents may not include any information that indicates the physical location of a student at a given time, other than attendance at a particular school, or participation in activities.

- Students may not have access to the district servers for posting or maintaining web sites. Access is restricted to authorized school employees only.

# Consistency of Web pages:

- Web pages may not contain any student e-mail address links, any survey-response links, or any other type of direct-response links.

- Credits for photographs must be given if a professional photographer does photography.

- Every reasonable attempt must be made to ensure that web pages are educationally sound and do not contain links to any questionable material or anything that can be deemed in violation of the Lyons Central School District policy.

- Student work may not be published without signed parental consent.

- Concern about the content of any page(s) created by students or staff should be directed to the building principal of that school.

- Given the rapid change in technology, some of the technical recommendations outlined in these standards may require change throughout the year. The District Technology Committee will make such changes with approval of the Technology Coordinator. These Web Page standards will be updated on an annual basis, or more frequently if required.

- Personal pages or links to personal pages cannot be linked to the district site.

- Advertising for businesses cannot be part of the district site.

Example:  Every reasonable attempt has been made to ensure that our web pages are educationally sound and do not contain links to any questionable material or anything that can be deemed in violation of the Lyons Central School District Web Page Standards Policy.

# Principal/District Approval Form

I understand that I am responsible for all material published on my school/site’s Web Page. I accept responsibility for review material to be posted in accordance with the district Web Page Standards. Each signed agreement will remain on file in my office.

Principal (Please print.) ______________________________

Signature _____________________________ Date    _____________

# Teacher/Web Publisher Agreement

I have fully read and understand the Lyons Central School District Web Page Standards. I have been informed of my responsibilities:

- Site development follows district guidelines.

- Site appropriately uses media – print and non-print.

- Copyright compliance is followed.

- Site is kept maintained and up to date.

- All material is screened before publication.

- All links are checked for accuracy and appropriateness.

- Approval for all materials is received from the principal before being posted.

I, the undersigned, acknowledge that I understand the policies and guidelines and that any uses I may make of materials for posting on a web site will be in accordance with both federal law and state law, as well as, district policies and standards. I understand any violations of the above provisions may result in disciplinary and/or legal action. I agree to report any misuse of electronic information resources to my school principal or district supervisor.

Teacher    ____________________________ Date ___________

School  ________________________________

# Parent Permission Form

(For use of student work or pictures On the Wayne Central School District Web Site)

Name of Student     _____________________________ ID___________________

Name of Parent ___________________________________

School Name  _____________________ Teacher Name ______________________

Your child’s teacher or another staff member is considering putting your child’s photo, writing, or art work onto our school home page. Because people can see this document all over the world, we are requesting your permission to display the work. For security reasons, only first names will be used and work will appear with a copyright notice prohibiting the copying of such work without express written permission. In the event anyone requests such permission, those requests will be forwarded to the parents. No home address or telephone will appear with such work. A copy of the picture or material is available. If you have any questions, please contact me.

I understand my child’s  writing, or artwork will be published on the World Wide Web in accordance to Lyons Central Schools Web Standards. My child’s work or photo will be removed immediately upon my request.

Student Name _____________________________________

Parent Signature __________________________ Date________________

Please sign and return as soon as possible. Thank You!

Appendix G. Loan of District Technology Equipment

All Loans are to be recorded and equipment is be returned upon request of someone from the Technology Department.  All equipment is to be used for classroom instructional purposes.  Digital cameras cannot be used by staff members for an extended period of time. (more than 2 weeks unless they are on permanent loan to a Department).  All equipment has to be returned before the end of the calendar school year in June.

It is also understood that equipment be returned in the same working condition which it was borrowed, allowing for reasonable wear and tear due to normal use.  The borrower assumes responsibility for any loss or damage beyond reasonable use.

Staff responsible for equipment:

Name:			Grade and Room no.

Building:			Phone

Date taking equipment 		Date expected to return

Please state in writing purpose or goal, project.

I will be financially responsible for equipment replacement if broken, stolen or lost.

Signature of staff taking equipment			Today’s Date

Approved:

Building Principal: 				Date:

Equipment Type:  Laptop		Digital camera            Digital camcorder

Model no.				Serial no.

Other items:

Memory cards, cables, chargers

Appendix H. Lyons Central School District

Loan of District Technology Equipment

In an effort to promote technology skill development among district staff, employees of LCSD are allowed to borrow district-owned equipment during extended vacations. It is necessary however, that such loans be on record and that equipment be returned either at the end of the vacation or upon request of someone from the Technology Department.

Note: Laptop computers are configured to work on the school network, they will not be altered to accommodate home internet access and nothing other than District owned software should be on the laptop.  Failure to comply with this regulation will be recorded in the employee’s personnel records.

Digital cameras have a two-week loan period on this equipment unless someone else makes a special request.

It is also understood that the equipment will be returned in the same working condition in which it was borrowed, allowing for reasonable “wear and tear" due to normal use. The borrower assumes responsibility for any loss or damage

beyond reasonable use.

Name of District staff 					Date of request

Date needed from      to

Equipment requested				        Additional materials

Please state in writing on the back of this form your purpose, goal, project, or research

Reasons with using this equipment .Evidence of increased use of technology in the classroom will be required.

I will be personally and financially responsible for this   equipment replacement if broken, stolen or lost.

Signature of Staff Taking Equipment

Todays Date

Approved:

Building Principal Date

Equipment:

Model #                                                                                         Serial Number